## Slide 1
NARXOZ UNIVERSITY / IT PROJECT MANAGEMENT / FINAL DEFENSE 2026
Aroma Lab
INTEGRATED COFFEE CHAIN ERP
From paper receipts and Excel sheets to a single web app —
POS, inventory and finance unified, built in 6 weeks.
REPO
github.com/R1nlary/aroma
Abay Akram, Shamen Bauyrzhan, Baidash Temirlan
01 / 08
AROMA LAB

## Slide 2
01 — CONTEXT
Manual chaos across 6 branches
PROBLEM
Paper, Excel, end-of-day counts.
Sales recorded on paper or standalone tills
Inventory counted manually at end of day
Invoices typed by accountant from receipts
No real-time view of revenue or food cost
SOLUTION
One web app, four modules, live data.
POS
INVENTORY
FINANCE
DASHBOARD
Single sale → auto stock deduction + invoice
Stock alerts: OK / Warning / Critical
Real-time KPI dashboard with charts
02 / 08
AROMA LAB

## Slide 3
02 — SCOPE & SCHEDULE
Six weeks, four milestones
6
WEEKS · MAR 15 – APR 29
4
MILESTONES · M1–M4
8
PAGES SHIPPED
ROLES
PM Planning, risks, docs
Full-Stack API, UI, DB, testing
UI/UX Landing, styling
Planning
1.5 wk
M1
Backend
2.5 wk
Frontend
3 wk
M2
Testing
1 wk
M3
Docs & Defense
1.5 wk
M4
03 / 08
AROMA LAB

## Slide 4
03 — FINANCIALS & RISK
Modest budget, fast payback, real risks
915K
KZT
TOTAL INVESTMENT
1.25M
KZT/yr
ANNUAL SAVINGS
9
months
PAYBACK PERIOD
+335K
KZT
YEAR-1 NET GAIN
TOP 3 RISKS (PROBABILITY × IMPACT)
R3
Time constraints
P4 · I5 · score 20
MVP-first; parallel docs; daily tracking
R1
Scope creep
P4 · I3 · score 12
Strict WBS; new asks go to backlog
R2
Technical complexity
P3 · I4 · score 12
Incremental dev; test each automation step
04 / 08
AROMA LAB

## Slide 5
04 — MVP
Eight pages, one automated flow
STACK
React 18 + Vite · Express · SQLite · JWT
Landing
Hero + contact form
Login
JWT auth · admin/1234
Admin
Product CRUD
POS
Grid · cart · receipt
Inventory
Stock alerts + POs
Finance
Invoices · VAT 12%
AUTOMATION
SALE
→
STOCK ↓
→
INVOICE
→
DASHBOARD ↑
LIVE DEMO · npm run dev → localhost:5173
05 / 08
AROMA LAB

## Slide 6
05 — RETROSPECTIVE
What worked, what didn't
WENT WELL
+
SQLite triggers handled stock + invoice in one transaction
+
MVP-first cut Mobile and 1C integration on time
+
JWT + bcrypt gave clean, testable auth from day one
+
Portable .db file made the demo bulletproof
TO IMPROVE
–
Automated tests were skipped — only manual checks
–
Dashboard built last — close call before defense
–
No CI/CD; deploy was local-only
–
Underestimated finance + VAT module effort
“
Cut scope ruthlessly, automate at the database layer, build the hardest module first.
06 / 08
AROMA LAB

## Slide 7
06 — CONCLUSION
Where we landed
PROBLEM
Paper + Excel across 6 branches → one web app
SCOPE
8 pages · 18 endpoints · 14 tables · 4 triggers
SCHEDULE
6 weeks · 4 milestones · delivered on time
BUDGET
915K KZT in · 1.25M KZT/yr out · 9-month payback
RISKS
5 tracked · R3 (time) was real, mitigated by MVP-first
MVP
POS → stock → invoice → dashboard, end-to-end
REPOSITORY
github.com/R1nlary/aroma
07 / 08
AROMA LAB

## Slide 8
Thank you.
Questions, comments, hard ones — ready.
REPO
github.com/R1nlary/aroma
DEMO
Login: admin / 1234 → POS demo flow
08 / 08
AROMA LAB